## Guidance
Safer Streets Fund Budget Toolkit
Bidding Tab - The table on this tab is locked for editting. The budgeted / actual costs is automatically populated based on the information that is provided on the Quarter 2 - Quarter 4 Projected Expenditure tabs. - Checks have been built in to ensure important information is captured. If the 'Expenditure Category' and the 'month' dropdown is not filled in, it will display an error message. - Please ensure you complete the information requested in Rows 22-29 Milestones and deliverables tab - This tab provides space for you to provide interim milestones against your individual project deliverables. Please provide details of the month, milestone and related deliverable (e.g. July, apply for planning permission, street lighting). This tab will be assessed as part of the question 'ability to deliver', so you are encouraged to ensure these are detailed and give assessors sufficient information to understand your delivery plans. The deliverables should align with the proposed deliverables in your application. You can expand this list if needed. Project Expenditure Tabs As part of your bid, we would like you to provide details of your project expenditure for each quarter. Project Expenditure Three types of information required here is: - Expenditure Type - Use the drop down to select the type of expenditure. We have provided 4 main categories - People (eg. project managers, staff), Equipment (eg, Doors, alleygates, street lights), Subcontracting (eg. arrangements with partners to deliver services or procure equipment), and Other (e.g. crime prevention publicity materials). For Equipment, Subcontracting and Other categories, a capital and non capital option is provided. PCCs should refer to their accounting rules on capitalisation in deciding which expenditure type to choose. - Service / Item Procurred - this should be drafted so that it is easy for assessors to understand how these purchases link to your proposed deliverables. - Budgeted / quoted amount. - Actual spend (does not need to be filled out in the initial application, but will be monitored during the grant period). i If you require more space on the space, drag the lever on the right hand corner of the table to expand the table. Matched resource tab Whilst we encourage areas to provide matched resource as part of their plan, it is not a requirement of funding and will not be assessed as part of your bid. However to assist us with quantifying the overall spend within plans and to inform our value for money assessments of the fund overall, we ask Bidders to provide an overview of any matched resource they will be providing and its value. Where this is not a financial contribution you are asked to provide both a high level quantification (e.g. number of staff hours) and estimated financial value. You can provide any further contextual information (e.g. if the matched resource will fall in future years) in the comments/further info column.

## Bidding
Safer Streets Fund | [6 empty] | NAME OF BIDDING ENTITY | [17 empty] | Checks
Reporting period: | People |  |  | Equipment (Expense) |  |  | Equipment (Capital) |  |  | Subcontracting (Expense) |  |  | Subcontracting (Capital) |  |  | Other (Expense) |  |  | Other (Capital) |  |  | Total
[25 empty] | Budgeted / Quoted Cost | Actual Cost
| Budget | Actual/Forecast | Variance | Budget | Actual/Forecast | Variance | Budget | Actual/Forecast | Variance | Budget | Actual/Forecast | Variance | Budget | Actual/Forecast | Variance | Budget | Actual/Forecast | Variance | Budget | Actual/Forecast | Variance | Budget | Actual/Forecast | Variance
Quarter 2
2020-07-01 | 7333 | 0 | -7333 | 0 | 0 | 0 | 90500 | 0 | -90500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97833 | 0 | -97833
2020-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | -1000 | 0 | 0 | 0 | 11500 | 0 | -11500 | 0 | 0 | 0 | 12500 | 0 | -12500
2020-09-01 | 0 | 0 | 0 | 49500 | 49500 | 0 | 14500 | 14500 | 0 | 13800 | 0 | -13800 | 0 | 0 | 0 | 34000 | 34000 | 0 | 0 | 0 | 0 | 111800 | 98000 | -13800
Q2 sub-total | 7333 | 0 | -7333 | 49500 | 49500 | 0 | 105000 | 14500 | -90500 | 14800 | 0 | -14800 | 0 | 0 | 0 | 45500 | 34000 | -11500 | 0 | 0 | 0 | 222133 | 98000 | -124133 |  | Pick the Expenditure Category +/or Month
Quarter 3
2020-10-01 | 7333 | 0 | -7333 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | -4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11333 | 0 | -11333
2020-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16500 | 0 | -16500 | 0 | 0 | 0 | 16500 | 0 | -16500
2020-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 243241.28 | 0 | -243241.28 | 7000 | 0 | -7000 | 0 | 0 | 0 | 15000 | 0 | -15000 | 0 | 0 | 0 | 265241.28 | 0 | -265241.28
Q3 sub-total | 7333 | 0 | -7333 | 0 | 0 | 0 | 243241.28 | 0 | -243241.28 | 11000 | 0 | -11000 | 0 | 0 | 0 | 31500 | 0 | -31500 | 0 | 0 | 0 | 293074.28 | 0 | -293074.28
Quarter 4
2021-01-01 | 7333 | 0 | -7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7333 | 0 | -7333
2021-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11500 | 0 | -11500 | 0 | 0 | 0 | 11500 | 0 | -11500
2021-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | -15000 | 0 | 0 | 0 | 15000 | 0 | -15000
Q4 sub-total | 7333 | 0 | -7333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26500 | 0 | -26500 | 0 | 0 | 0 | 33833 | 0 | -33833
Total | 21999 | 0 | -21999 | 49500 | 49500 | 0 | 348241.28 | 14500 | -333741.28 | 25800 | 0 | -25800 | 0 | 0 | 0 | 103500 | 34000 | -69500 | 0 | 0 | 0 | 549040.28 | 98000 | -451040.28
Completed by: | XXXXXXXXXXX
Date Updated: | 11th March
Contact | XXXXXXXXXXX
Email address | XXXXXXXXXXX
Grant allocation agreed
Address
Supplier Code

## Milestones and deliverables
Safer Streets Fund |  |  | NAME OF BIDDING ENTITY
| Month | Milestone | Related deliverable
| July | Purchase of 14 Deployable CCTV camera's with 5 year maintenance, support & airtime agreement | Deployable CCTV
| August | Removal of Graffiti on empty buildings in main square | Graffiti removal
| August | Purchase of Literature for crime prevention workshops | Crime prevention workshops and publicity materials
| September | Replace 12 current lamppost with 8m posts capable of hosting deployable CCTV | Additional lighting and installation of suitable lampposts capable of hosting deployable CCTV
| September | Pruning and lifting of selected tree canopy's | Tree and shrub maintenance to improve natural surveillance
| September | Start of improvements to current lighting in areas identified during Q1 | Improved lighting
| September | Purchase of first batch of home security packes to support the crime prevention workshops | Crime prevention workshops and publicity materials
| October | 7ft high metal gate & fencing installed between No 8 Yardley & Hillfileds House | Gating alleyways
| September | Running crime prevention workshops and community engagement from current community centres in the area | Crime prevention workshops and publicity materials
| December | Continued crime prevention workshops and community engagement from current community centres in the area | Crime prevention workshops and publicity materials
| December | Up grade and renewal of CCTV equipment to current standard to allow coverage of identified area. Including 5 year maintenance and support package | Fixed CCTV
| December | Removal of the brick planters, which are in poor condition and remove landscaping to increase natural surveillance of the area. | Removal of raised shrub beds and walls that act as focal points for crime
| March | Removal of two phone boxes | Removal of telephone kiosks
| March | Final run of communty workshops in local venues | Crime prevention workshops and publicity materials

## Projected Expenditure - Qtr2
Safer Streets Fund | NAME OF BIDDING ENTITY
Qtr 2: Jul-Sept
Projected Expenditure
Expenditure Category | Month | Service / Item Procurred | Budgeted / Quoted Cost | Actual Cost
Equipment (Capital) | 2020-07-01 | Purchase of 14 Deployable CCTV camera's with 5 year maintenance, support & airtime agreement | 90500
People | 2020-07-01 | Project officer based with PCC | 7333
Subcontracting (Expense) | 2020-08-01 | Removal of Graffiti on buildings in main square | 1000
Other (Expense) | 2020-08-01 | Overheads | 11500
Equipment (Capital) | 2020-09-01 | Replace 12 current lamppost with 8m posts capable of hosting deployable CCTV | 14000
Equipment (Capital) | 2020-09-01 | New brackets to 2 existing lampposts capable of hosting deployable CCTV | 500
Equipment (Expense) | 2020-09-01 | Upgraded lighting across area including new lanterns and associated cabling where required | 48000
Subcontracting (Expense) | 2020-09-01 | Tree and shrub maintenance to improve natural surveillance in residential areas and main square | 2800
Other (Expense) | 2020-09-01 | Addition of artwork to empty shop fronts to enhance the area and encourage footfall. | 4000
Subcontracting (Expense) | 2020-09-01 | Floor painting of roads, games and playground activities to enhance the area and encourage use by local children and Harmony family hub | 11000
Equipment (Expense) | 2020-09-01 | 2 laptops for use with CCTV system allowing local access to camera feed in required | 1500
Other (Expense) | 2020-09-01 | Home security packs for residents, to include locks, timers, alarms | 10000
Other (Expense) | 2020-09-01 | Literature and publicity material supporting crime prevention | 5000
Other (Expense) | 2020-09-01 | Running crime prevention workshops and community engagement from community centres in the area | 15000
Total Budget/Actual Spend for the Quarter |  |  | 222133 | 0

## Projected Expenditure - Qtr3
Safer Streets Fund | NAME OF BIDDING ENTITY
Qtr 3: Oct-Dec
Projected Expenditure
Expenditure Category | Month | Service / Item Procurred | Budgeted / Quoted Cost | Actual Cost
People | 2020-10-01 | Project officer based with PCC | 7333
Subcontracting (Expense) | 2020-10-01 | 7ft high metal gate & fencing installed between No 8 Yardley & Hillfileds House | 4000
Other (Expense) | 2020-11-01 | Home security packs for residents, to include locks, timers, alarms | 5000
Other (Expense) | 2020-11-01 | Overheads | 11500
Other (Expense) | 2020-12-01 | Running crime prevention workshops and community engagement from community centres in the area | 15000
Subcontracting (Expense) | 2020-12-01 | Removal of the brick planters, which are in poor condition and remove landscaping to increase natural surveillance of the area. | 3000
Subcontracting (Expense) | 2020-12-01 | Removal of derelict wall to improve area and enhance pathway | 4000
Equipment (Capital) | 2020-12-01 | Up grading and additional fixed CCTV equipment | 243241.28
Total Budget/Actual Spend for the Quarter |  |  | 293074.28 | 0

## Projected Expenditure - Qtr4
Safer Streets Fund | NAME OF BIDDING ENTITY
Qtr 4: Jan-March
Projected Expenditure
Expenditure Category | Month | Service / Item Procurred | Budgeted / Quoted Cost | Actual Cost
People | 2021-01-01 | Project officer based with PCC | 7333
Other (Expense) | 2021-02-01 | Overheads | 11500
Other (Expense) | 2021-03-01 | Running crime prevention workshops and community engagement from community centres in the area | 15000
Total Budget/Actual Spend for the Quarter |  |  | 33833 | 0

## Matched resource
Service/item | Estimated value | Comments/further info
Tree and shrub maintenance to improve natural surveillance | 5000
Project support (Coventry City Council Staff) | 10000
CCTV Monitoring via current control room (Est) | 10000
Community engagement | 5000
Management support | 2000